## Slide 1
BPMS 1.0 SFU FPGA
Project Methodology
Roles, gates, and the architect workflow
Marco Pausini | 28 April 2026
Architect / sponsor
Agree on schedule and methodology
RTL designer
Agree on spec template + handoff contract
DV
Agree on what gets consumed at G5
Notes: Open with what's at stake: by end of this meeting we want to leave with M1 committed, or pushed back with reasons; ADR-0005 either accepted or with the exact blocker named; and the spec template confirmed. Set the expectation that the bulk of the talk is the architect workflow because that is what we are committing to deliver against.

## Slide 2
Why now + what is new
Frame
outline v0.2
Key message: the framework was specification-only. The execution layer makes the schedule real and aligns with the RTL flow.
Before: specification layer only
FAD
MS
ICD
ADR
RTM
After: spec layer + execution layer
Spec layer
FAD · MS · ICD · ADR · RTM
Execution layer
01–05 methodology docs
flow · gates · evidence
Started with arch/: good for what to write; silent on how to build it.
Need to align with RTL designer’s Claude Code assisted flow.
Schedule needs grounding in methodology, not folder layout.
Notes: Keep this short. The point is to motivate why this is not just a template discussion. The system architect asked for a delivery date; that date needs a methodology and an execution model.

## Slide 3
Two-layer framework + project phases
Methodology
01-fpga-project-methodology.md §2–§3
Layer | Location | Key docs | Owner
Spec | arch/ | FAD, MS, ICD, ADR, RTM | Architect
Execution | docs/methodology/ | 01–05-*.md | Shared, architect-led
# | Phase | Key gate
1 | Architecture | G1, G2, G3
2 | Module specification | G4a
3 | RTL implementation | G4b + integration
4 | Integration | implementation sign-off
5 | HW bring-up | bring-up sign-off
Dependency flow
Architecture
Module specs
RTL
Integration
Bring-up
Gates, not calendars, control promotion. Phases may overlap only when upstream artefacts are stable enough for the next consumer.
Notes: This folder defines what the architecture is; the methodology docs define how it gets built. Resist requests to merge them. The split allows specification to baseline before tooling is finalised. Phases overlap, but gates control promotion.

## Slide 4
Repo layout: flat by artefact type
Methodology
01-fpga-project-methodology.md §4
bpms-sfu-fpga-design/
arch/ # FAD, module specs, ICD, ADR, RTM
rtl/ # SystemVerilog sources
model/ # Python bit-exact reference models
tb/ # unit testbenches
constraints/ # XDC + OOC constraints
prj/ # Vivado project/IP recreation
scripts/ # Make/Tcl/CI/lint/doc_check
docs/methodology/ # execution layer
reports/ # generated evidence
waivers/ # lint/CDC/timing waivers
Boundary points
model/ is architect-owned for DSP/numerical reference models.
tb/ is unit-level, authored alongside specs and RTL.
Verification repo consumes arch/ read-only.
Principles
Flat by artefact type, not lifecycle phase.
Design and verification are separate repos.
Reports are regenerated/archived by commit hash.
Waivers are version-controlled.
Notes: Three points only: flat by artefact type, design and verification are separate repos, and reference models live with specs because they make bit-exact acceptance enforceable.

## Slide 5
Gate reference card
Methodology
05-signoff-criteria.md §11–§14
Key message: this is the shared vocabulary for the rest of the talk.
Gate | Trigger | Owner | What passes
G1 Orient | FAD §1–§6 complete | Architect | Scope, boundary, block diagram, clocking, module inventory consistent
G2 Contracts | FAD §7–§8 + core ICDs ready | Architect | Interface conventions, fixed-point policy, ICDs frozen
G3 Budgets | FAD §9–§12 complete | Architect | Latency/resource/floorplan/power budgets populated or TBD-with-owner
G4a Spec sign-off | Per MS draft complete | Architect | MS reaches design_ready; design_ready_blocking empty
G4b uArch + RTL sign-off | Per module RTL ready | RTL Designer | uArch authored; lint/sim/OOC/CDC green; MS §12.3 evidence populated
Integration | Per module | RTL Designer | MS §12.3 pass; module-level XDC merged
G5 Handoff to DV | Tagged commit | Verification Engineer | DV consumes without architect follow-up
Use this as the reference card whenever later slides mention G1–G5.
Notes: This slide is intentionally a reference card. It keeps the rest of the deck short: when a later slide says G4a or G5, point back here instead of re-explaining the gate.

## Slide 6
Three roles, three sets of artefacts
Roles
01-fpga-project-methodology.md §1
Roles define work-product ownership. They are not org-chart positions.
Role | Owns | Gates owned
FPGA Architect | FAD, MS, ICD, ADR, RTM, refmodels (DSP) | G1, G2, G3, G4a
RTL Designer | uArch, RTL source, unit TBs, implementation evidence | G4b, integration
Verification Engineer | UVM env, integration TB, coverage closure | G5
Important boundary
The architect does not own the uArch document. That is deliberate: the architect owns the external contract; the designer owns the internal implementation.
Notes: Note explicitly: the architect does not own the uArch document. That is a deliberate role boundary, codified in ADR-0005. A single person may fill multiple roles; the boundary is about artefacts.

## Slide 7
The spec/uArch split (ADR-0005)
Roles
01-fpga-project-methodology.md §3.1
Key message: MS is what the block does externally. uArch is how it does it internally.
 | Module Spec (MS) | Micro-Architecture (uArch)
Filename | arch/modules/<m>.md | designer choice, e.g. rtl/<m>/uarch.md
Owner | Architect | RTL Designer
Scope | External contract | Internal implementation
Gate | G4a | G4b
Granularity | Functional block (~10 for SFU) | One or more .sv files inside the block
Examples | ports, interfaces, clocks, registers, operation, performance, errors, test hooks, refmodel pointer | FSMs, pipeline depth, FIFO depths, sub-block decomposition, internal Q-formats
Notes: Spend about 90 seconds here. This is the slide everyone needs to remember. The SFU's functional blocks may decompose into multiple SystemVerilog files; the architect does not dictate that decomposition.

## Slide 8
Reference model ownership + why the split matters
Roles
02-architect-workflow.md §1.1, §5
Refmodel ownership
Refmodels live in model/<m>/ in the design repo.
Bit-exactness policy stated in MS §3.3: bit_exact / ulp_bounded(N) / not_applicable.
Designer unit TB correlates RTL against refmodel sample-by-sample.
Vendor IP wrappers use boundary metrics instead.
Why this matters
Architect baselines contracts before implementation starts.
DV can build TBs in parallel with RTL.
Designer keeps freedom on internal choices.
External questions belong in MS; internal questions belong in uArch.
Notes: This is the answer to how bit-exact is made enforceable. The architect signs the refmodel as authoritative. If the designer asks what the block outputs when input is X, it is a module spec question. If the designer asks what the FSM looks like, it is a uArch question.

## Slide 9
Architect workflow at a glance
Workflow
02-architect-workflow.md §1–§2
Inputs | Outputs | Gates
ARCH-001 v2.4 SFU-001 v1.6 Vendor docs Filter bank spec | 1 FAD ~10 MSs ~5 ICDs ADRs as needed 1 living RTM Refmodels for DSP blocks | G1 Orient G2 Contracts G3 Budgets G4a Spec sign-off Consistency review at G4b
Authoring dependency order
FAD §1–§6
Orient
Core ICDs
streaming/register/OBG
FAD §7–§12
contracts + budgets
Module Specs
one per block
RTM
living
Notes: Set the scope before the mechanics. ICDs come between orient sections and contracts/budgets sections because module specs need frozen ICDs and contract sections reference them.

## Slide 10
Section-by-section drafting: markers + citation
Workflow
02-architect-workflow.md §3–§4
Drafting cadence
Before | During | After
1. Identify target section 2. Gather source material 3. List specified / inferred / proposed | 4. Fill template + cite 5. Mark every gap 6. Identify ADR triggers 7. Identify cross-refs | 8. Self-check gate 9. Independent review 10. Revise + commit
Sections, not whole documents, are the unit of review, revision, and commit.
Markers and citation rule
[TBD: <reason>, <owner>]
[STUB: <blocking item>]
[ASSUMPTION: <text>, <expiry trigger>]
[INFERRED from <source §>]
Every factual claim from a parent doc carries an inline citation: (SFU-001 §6.4). Otherwise mark as [INFERRED] or [ASSUMPTION].
Notes: The cadence sets the operating tempo: section-sized work units, each closed before moving on. The markers are greppable. Citations are the anti-laundering principle: with LLMs in the pipeline, the failure mode is plausible but wrong text.

## Slide 11
Architecture invariants and functional boundary
Workflow
02-architect-workflow.md §4.3–§4.5
Some constraints apply across the entire design. The DCU/SFU ownership boundary is one of them.
Invariants
FAD §1.5 lists project-wide invariants.
No FAD section, MS, ICD, or ADR may violate them.
The architect enforces invariants across all downstream artefacts.
Boundary-crossing procedure
Open an ADR.
Cite the system-level source that justifies the change.
If no source exists → reject by default.
Example: per-beam Doppler in the SFU is a red flag; DCU owns beam-level functions unless an ADR proves otherwise.
Notes: Concrete example: anything that looks like per-beam Doppler in the SFU is an immediate red flag. The DCU owns it. Moving that boundary requires an ADR with explicit system-level justification.

## Slide 12
Design-ready criteria: the G4a checklist
Workflow
02-architect-workflow.md §5
Checklist
clock domains · interfaces · parameters · register set · operation · performance · error/status · system constraints · test hooks · refmodel
Completeness test
Could a senior RTL designer implement this module from the spec + referenced ICDs, making their own micro-architecture choices, without asking the architect a question about intended external behaviour?
If no — not_design_ready.
Notes: Read the completeness test out loud. This is the line we will use repeatedly over the next 6 weeks. It also protects against scope creep into uArch. Pre-align with Gastón before the meeting; if he disagrees with this test, the methodology shifts.

## Slide 13
What the MS does NOT prescribe + common failure modes
Workflow
02-architect-workflow.md §5.2–§5.4
Not in the MS — uArch territory
FSMs / state-machine internals
Pipeline depth or staging
FIFO implementation details
Internal sub-block decomposition
Internal fixed-point precision
Register address/bit assignment
Common failure modes
Failure | Fix
Ambiguous backpressure | Specify stall / drop / error
Performance target without number | State cycles or ns
Error listed but behaviour undefined | Specify status / interrupt / output
Spec prescribes FSM or pipeline | Remove; state external constraint
Notes: The last failure mode is the most common for architects coming from RTL. Only boundary fixed-point formats are in the MS. Internal precision is a designer choice unless it observably violates a refmodel-defined acceptance criterion.

## Slide 14
LLM-assisted workflow: roles + pipeline
Workflow
01-fpga-project-methodology.md §5; 02-architect-workflow.md §6
Role | Tool | Purpose
fpga_arch | Claude.ai | Draft sections from sources
fpga_arch_reviewer | ChatGPT | Adversarial review
repo_operator | Claude Code | Repo-aware edits + checks
Pipeline
A. Draft
section + citations + markers
B. Review
issue table by severity
C. Decide
accept / reject / defer
D. Apply
minimal diffs
E. Check
cross-refs, frontmatter, RTM
Sign-off authority: human only.
Notes: Even when an LLM-generated artefact looks polished and complete, no LLM signs off. Steps B and E use LLMs with no rewrite authority. Step D writes to the repo only from accepted review items.

## Slide 15
Live demo: real reviewer issue table
Workflow
02-architect-workflow.md §6.4
Reviews come back as an issue table, not rewritten prose.
Severity | Location | Issue | Action | Gate
blocker | FAD §4.5 | CDC Aurora→DSP unspecified | Add async FIFO row, depth, owner | G1 / CDC
high | spec §Performance | Band gain Q-format undefined | Specify Q(a.b) and saturation rule | G4a
medium | spec §Operation | Reset-while-busy missing | Add drop/complete/error spec | G4a
Operating rule
The engineer decides: accepted / rejected / deferred. Accepted items become minimal diffs in the repo.
Notes: This is the demo slide. Pull a real three-row excerpt from an existing review if available. Walk through one row and show how it became a commit. If no real review exists before deck build, run one against the current FAD section and replace this table.

## Slide 16
Architect at G4b + later phases
Workflow
05-signoff-criteria.md §12.2–§15
Architect at G4b reviews for
Implementation respects the MS contract.
CDC mechanisms match MS and FAD §4.5.
Resource usage is within FAD §9.2 budget.
No undocumented functional boundary crossing.
Later-phase responsibilities
Phase 3 RTL: integration questions, post-synth budgets, ADRs.
Phase 4 integration: top constraints, CDC reports, timing adjudication.
Phase 5 bring-up: sequence, hardware validation evidence.
G4a is the architect gate. G4b is the designer gate. Architect remains engaged for consistency, not re-implementation.
Notes: Designer does not reach into the spec; architect does not reach into the implementation. Exception: implementation evidence reveals a missing constraint, which goes back into the MS or an ADR. Architect bandwidth does not drop to zero after Phase 2.

## Slide 17
Execution flow: build entrypoints and gate commands
Execution
04-execution-flow.md §3
Single make-based flow wraps Vivado, simulator, and lint. Every stage has a target, report, and sign-off reference.
Target | Stage | Sign-off ref
make doc_check | Documentation gate | §3
make lint MOD=<m> | RTL lint | §4
make sim_unit MOD=<m> | Unit sim, incl. refmodel correlation | §5
make synth_ooc MOD=<m> | OOC synthesis | §6
make cdc MOD=<m> | CDC check | §7
make synth_top / impl / timing | Top synth + implementation | §8–§10
Evidence rule
Reports archive under reports/<commit-hash>/; each gate references the exact commit where evidence was captured.
Notes: This is the how-to-run-the-build layer. Two principles: every stage produces an archived report at a commit hash, and each gate command cross-references the matching pass criteria in the sign-off document. No manual Vivado clicks as sign-off evidence.

## Slide 18
Sign-off criteria: gate map
Execution
05-signoff-criteria.md §2
Every artefact has a defined passing definition. Sign-off remains human responsibility.
G1
G2
G3
G4a
G4b
integ.
G5
HW
Architecture
Spec / refmodel
RTL lint
Unit sim
OOC synth
CDC
Constraints
Top synth
Implementation
DV / UVM
HW bring-up
●
●
●
●
●
●
●
●
●
●
●
●
●
●
●
Rule
No gate may be waived silently: architecture waivers are ADRs; tool waivers live under waivers/.
Notes: Walk through one column, e.g. G4a means spec sign-off per module and MS reaches design_ready. Each gate has a dedicated sign-off criteria section. Waivers are explicit and reviewed at the gate they affect.

## Slide 19
CI regression levels + waiver discipline
Execution
04-execution-flow.md §13–§15
CI levels
Level | Trigger | Wall-clock
L0 | Pre-commit | < 1 min
L1 | Push to feature branch | < 15 min
L2 | PR open / update | < 30 min
L3 | Nightly | < 6 h
L4 | Release candidate | < 12 h
Waiver discipline
Stored under waivers/ for lint, CDC, and timing.
Required: ID, citation to analysis or ADR, expiry trigger.
A waiver without an expiry trigger blocks integration.
Reviewed at the gate it affects.
Notes: The CI level grid makes the methodology executable. Each level builds on the previous one. Waiver discipline is the implementation-side version of citation discipline: visible, version-controlled, with expiry.

## Slide 20
Schedule
Schedule
outline v0.2
Two milestones, six weeks total. LLM-assisted estimate; manual baseline would be ~10–12 weeks.
Milestone | Outputs | Target
M1 | FAD §1–§12 baselined; core ICDs frozen; ADR-0005 accepted; pilot MS drafted end-to-end | 2 weeks
M2 | All MSs at design_ready; RTM populated; architecture officially done | +4 weeks / 6 total
Contingencies
Gastón’s spec template confirmation by end of week 1.
Source-doc open issues OI-001, OI-S07, OI-S08 assigned owners.
No major architectural surprises in FAD §3–§5.
Notes: State the LLM speedup honestly. LLMs accelerate drafting, consistency checks, scaffolding, and format work. They do not speed up engineering thinking, ambiguity resolution, or stakeholder alignment. The six-week estimate assumes all three contingencies hold.

## Slide 21
Decisions to surface and asks per attendee
Schedule
outline v0.2
Decisions to surface
Decision | Status | Resolves with
ADR-0005 spec/uArch split | Proposed | Gastón template confirmation
FAD §6 module inventory | Pending update | G1 review pass
Reviewer configuration | Pending | Architect this week
Source-doc OIs | Open | Owner assignment
M1+M2 schedule | Proposed | Sponsor agreement
Asks
Gastón — confirm spec template by Fri 8 May 2026.
Shlomi — assign owners to OI-001, OI-S07, OI-S08 by Fri 15 May 2026.
Internal team — agree review cadence and reviewer LLM tool in this meeting.
End on concrete decisions, owners, and dates. Adjust dates if the meeting slips.
Notes: End on the asks. Be specific. The suggested dates assume today's date of 28 April 2026. If the meeting slips, all dates slip together.